## Sheet1
Organisation Name | Service Name | Organisation Type | Connection Type | A-end PoP | B-end Postcode | Organisation Postcode | Bandwidth (Mbit/s) | Cutover | Comment
Canterbury Christ Church University | Tunbridge Wells Campus | HE | Primary |  | TN3 0TG | CT1 1QU | 100 | 2011-06-16
Canterbury Christ Church University | Broadstairs Campus | HE | Primary |  | CT10 2WA | CT1 1QU | 1000 | 2011-06-14
Canterbury Christ Church University | Folkestone Campus | HE | Primary |  | CT20 1JG | CT1 1QU | 100 | 2011-06-28
Canterbury Christ Church University | Canterbury Campus | HE | Primary |  | CT1 1UT | CT1 1QU | 1000 | 2011-08-04 | Temporary solution - awaiting supercore
Canterbury College | N/A | FE | Primary |  | CT1 3AJ | CT1 3AJ | 1000 | 2011-04-20 | Existing 100Mbps retained until supercore ready
Dorton College of Further Education | N/A | FE | Primary |  | TN15 0EB | TN15 0EB | 100 | 2011-05-25
Hadlow College | Canterbury Campus | FE | Primary |  | CT1 1TB | TN11 0AL | 10 | 2011-06-17
Hadlow College | Mottingham Campus | FE | Primary |  | SE12 9AW | TN11 0AL | 10 | 2011-05-27
Hadlow College | Tonbridge Campus | FE | Primary |  | TN11 0AL | TN11 0AL | 100 | 2011-06-10
Hilderstone College | N/A | FE | Primary |  | CT10 2JW | CT10 2JW | 100 | 2011-06-07
IFS School of Finance | Kent Campus | Other | Primary |  | CT1 2XJ | EC3R 8LJ | 20/100 | 2011-06-30
K College ( formerly South Kent College ) | Ashford Campus | FE | Primary |  | TN23 4RJ | TN9 2PW | 100 | 2011-07-05
K College ( formerly West Kent College ) | Tonbridge Campus | FE | Primary |  | TN9 2PW | TN9 2PW | 100 | 2011-06-03
Medway Council | N/A | LA | Primary |  | ME4 4TR | ME4 4TR | 200/1000 | 2011-08-09
Mid-Kent College of Higher and Further Education | N/A | FE | Primary |  | ME7 1FN | ME7 1FN | 1000 | 2011-07-21 | Cutover on existing 100Mbps circuit - upgrade to 1Gbps delivered on 04/11/2011
North West Kent College of Technology | N/A | FE | Primary |  | DA1 2JT | DA1 2JT | 100 | 2011-05-17
Thanet College | N/A | FE | Primary |  | CT10 1PN | CT10 1PN | 100 | 2011-06-08
The Universities at Medway | N/A | HE | Primary |  | ME4 4TB | SE10 9LS | 2000 | 2011-08-03
University of Kent | Canterbury Campus | HE | Primary |  | CT2 7NF | CT2 7NF | 6000 | 2011-08-02
University of Kent | Tonbridge Campus | HE | Primary |  | TN9 1TG | CT2 7NF | 100 | 2011-11-24 | originally migrated in June 2011 using a VPN tunnel via CCCU Salomons
University for the Creative Arts | Canterbury Campus | HE | Primary |  | CT1 3AN | ME16 8AG | 100 | 2011-06-29 | Awaiting supercore ( using interim connection )
University for the Creative Arts | Chatham Campus | HE | Primary |  | ME4 4TZ | ME16 8AG | 100 | 2011-07-07
University for the Creative Arts | Maidstone Campus | HE | Primary |  | ME16 8AG | ME16 8AG | 100 | 2011-05-19
University for the Creative Arts | Rochester Campus | HE | Primary |  | ME1 1DZ | ME16 8AG | 100 | 2011-07-21
Workers' Educational Association | Rochester Campus | WEA | Primary |  | ME2 4DP | EC2A 4HB | 10 | 2011-07-12